## Burndown Chart
Sprint Burndown Chart
Sprint 1
Task ID | Task Description | Initial Estimate | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Team Building | 1 | 1
2 | Preparation and team discussion of the project assignment | 4 |  |  | 2 | 2
3 | WorldEdit setup | 1 |  |  |  |  | 1
Completed Effort |  | 0 | 1 | 0 | 2 | 2 | 1
Remaining Effort |  | 6 | 5 | 5 | 3 | 1 | 0
Ideal Burndown |  | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0