## Burndown Chart
Sprint Burndown Chart
Sprint 1
Task ID | Task Description | Initial Estimate | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Git setup | 1 | 1
2 | Meeting to prepare Milestone 1 – User Stories | 1 |  |  | 1
3 | User Stories Brainstorming | 4 | 1 | 1 | 1 | 1
4 | Meeting to choose and vote for the best User Stories to deliver | 1 |  |  |  |  | 1
Completed Effort |  | 0 | 2 | 1 | 2 | 1 | 1
Remaining Effort |  | 7 | 5 | 4 | 2 | 1 | 0
Ideal Burndown |  | 7 | 5.6 | 4.2 | 2.8 | 1.4 | 0