## Burndown Chart
Sprint Burndown Chart
Sprint 3
Task ID | Task Description | Initial Estimate | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Discussion to analise the work to do in Milestone2 | 1 |  |  |  |  | 1
Completed Effort |  | 0 | 0 | 0 | 0 | 0 | 1
Remaining Effort |  | 1 | 1 | 1 | 1 | 1 | 0
Ideal Burndown |  | 1 | 0.8 | 0.6 | 0.4 | 0.2 | 0