## Burndown Chart
Sprint Burndown Chart
Sprint 4
Task ID | Task Description | Initial Estimate | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Working for Milestone 2 | 4 | 1 | 1 | 1 | 1
2 | Distributed what each member reviews for Milestone 2 | 1 |  | 1
Completed Effort |  | 0 | 1 | 2 | 1 | 1 | 0
Remaining Effort |  | 5 | 4 | 2 | 1 | 0 | 0
Ideal Burndown |  | 5 | 4 | 3 | 2 | 1 | 0