## Burndown Chart
Sprint Burndown Chart
Sprint 5
Task ID | Task Description | Initial Estimate | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Individual work | 7 | 1.5 | 1.5 | 2 | 1 | 1
2 | Group work session - Milestone 2 deliver | 6 | 0 | 0 | 6 | 0 | 0
3 | Meeting to clarify next goals for Milestone 3 | 2 | 0 | 0 | 0 | 2 | 0
Completed Effort |  | 0 | 1.5 | 1.5 | 8 | 3 | 1
Remaining Effort |  | 15 | 13.5 | 12 | 4 | 1 | 0
Ideal Burndown |  | 15 | 12 | 9 | 6 | 3 | 0