## Burndown Chart
Sprint Burndown Chart
Sprint 6
Task ID | Task Description | Initial Estimate | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Meeting: details to improve regarding previous milestones | 1 |  | 1
2 | Meeting: organization for milestone 3 | 2 |  | 1 |  | 1
3 | Meeting: division of tasks for milestone 3. | 1 |  | 1
4 | Brainstorm on the existing code to achieve the US at milestone 3 | 4 |  | 1 | 1 | 1 | 1
5 | Start of user stories for milestone3. | 3 |  |  | 1 | 1 | 1
6 | Planning for the next few weeks. How should we organize ourselves in order to achieve all milestone 3 objectives. | 1 |  | 1
Completed Effort |  | 0 | 0 | 5 | 2 | 3 | 2
Remaining Effort |  | 12 | 12 | 7 | 5 | 2 | 0
Ideal Burndown |  | 12 | 9.6 | 7.2 | 4.8 | 2.4 | 0