## Burndown Chart
Sprint Burndown Chart
Sprint 7
Task ID | Task Description | Initial Estimate | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Group work session - Each member's worldEdit extension shared with the team. | 2 | 2 | 0 | 0 | 0 | 0
2 | Asynchronous work: MileStone 3 deliverables. | 3 | 0 | 2 | 1 | 0 | 0
3 | Group work session to work on Milestone 3 and edit the Demo Video. | 3 | 0 | 0 | 1 | 2 | 0
Completed Effort |  | 0 | 2 | 2 | 2 | 2 | 0
Remaining Effort |  | 8 | 6 | 4 | 2 | 0 | 0
Ideal Burndown |  | 8 | 6.4 | 4.8 | 3.2 | 1.6 | 0