## Burndown Chart
Sprint Burndown Chart
Sprint 6
Task ID | Task Description | Initial Estimate | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Development of the US VULCANO for milestone3. | 3 | 2 | 1
2 | Development of the US RIFT for milestone3. | 3 | 1 | 2
3 | Development of the US CLIMATE CHANGES for milestone3. | 3 | 1 | 2
4 | Group work session - Each member's worldEdit extension shared with the team. | 1 |  | 1
5 | Group work session to work on Milestone 3 and edit the Demo Video. | 2 |  |  |  |  | 2
6 | Project delivery | 1 |  |  |  |  | 1
7 | Create merged review log book | 1 |  |  |  |  | 1
8 | Project report | 5 | 1 | 1 | 1 | 1 | 1
Completed Effort |  | 0 | 5 | 7 | 1 | 1 | 5
Remaining Effort |  | 19 | 14 | 7 | 6 | 5 | 0
Ideal Burndown |  | 19 | 15.2 | 11.4 | 7.6 | 3.8 | 0