## Week 1
Task ID | Task Description
1 | Team Building
2 | Preparation and team discussion of the project assignment
3 | WorldEdit setup

## Week 2
Task ID | Task Description
1 | Git setup
2 | Meeting to prepare Milestone 1 – User Stories
3 | User Stories Brainstorming
4 | Meeting to choose and vote for the best User Stories to deliver

## Work 3
Task ID | Task Description
1 | Discussion to analyse the work to do in Milestone2

## Week 4
Task ID | Task Description
1 | Continue work for Milestone 2
2 | Distributed what each member reviews for Milestone 2

## Week 5
Task ID | Task Description
1 | Individual work
2 | Group work session - Milestone 2 deliver
3 | Meeting to clarify next goals for Milestone 3

## Week 6
Task ID | Task Description
1 | Meeting: details to improve regarding previous milestones
2 | Meeting: organization for milestone 3
3 | Meeting: division of tasks for milestone 3.
4 | Brainstorm on the existing code to achieve the US at milestone 3
5 | Start of user stories for milestone3.
6 | Planning for the next few weeks. How should we organize ourselves in order to achieve all milestone 3 objectives.

## Week 7
Task ID | Task Description
1 | Group work session - Each member's worldEdit extension shared with the team.
2 | Asynchronous work: MileStone 3 deliverables.
3 | Group work session to work on Milestone 3 and edit the Demo Video.

## Week 8
Task ID | Task Description | Done
1 | Development of the US VULCANO for milestone3. | x
2 | Development of the US RIFT for milestone3. | x
3 | Development of the US CLIMATE CHANGES for milestone3. | x
4 | Group work session - Each member's worldEdit extension shared with the team. | x
5 | Group work session to work on Milestone 3 and edit the Demo Video. | x
6 | Project delivery
7 | Create merged review log book | x
8 | Project report | x